## Sheet1
Seattle Department of Transportation
Bridging the Gap Planned Accomplishments
| Parameter |  | Value
| Group By: |  | Program |  |  |  |  | Annual target has been met or exeeded |  |  | 40 accomplishment types are green
| Year: |  | 2009 |  |  |  |  | Annual target is on track to be met |  |  | 0 accomplishment types are light green
| Division: |  | All |  |  |  |  | Annual target is on track with caution |  |  | 0 accomplishment types are yellow
| Program: |  | All |  |  |  |  | Annual target will not be met |  |  | 1 accomplishment types are red
| Run Date: |  | 2009-12-31 10:57
Program |  |  |  | Division | Project # | Project Name | Accomplishment |  | Unit of Measure | Work Plan Target | Q1 Total |  | Q2 Total |  |  | Q3 Total |  |  | Q4 Total |  |  |  | YTD Total
Commuter Mobility |  |  |  | Traffic Management | TG356560 | Traffic Operations Spot Improvements - Signals | Electrical traffic control devices evaluated |  | Count | 200 | 144 |  | 80 |  |  | 61 |  |  | 11 |  |  |  | 296
Commuter Mobility |  |  |  | Traffic Management | TG356560 | Traffic Operations Spot Improvements - Signals | Electrical traffic control devices installed, modified or removed |  | Count | 50 | 16 |  | 8 |  |  | 16 |  |  | 10 |  |  |  | 50
Commuter Mobility |  |  |  | Policy and Planning | TG357040 | Transit Service | Secured transit hours |  | Count | 8,800 | 0 |  | 0 |  |  | 8800 |  |  | 0 |  |  |  | 8800
Commuter Mobility |  |  |  | Traffic Management | TG356570 | Traffic Operations Spot Improvements | Speed watch trailer deployed |  | Times | 65 | 10 |  | 25 |  |  | 34 |  |  | 4 |  |  |  | 73
Commuter Mobility |  |  |  | Traffic Management | TG356570 | Traffic Operations Spot Improvements | Traffic control concerns evaluated |  | Count | 500 | 163 |  | 131 |  |  | 145 |  |  | 63 |  |  |  | 502
Corridor and Intersection Improvements |  |  |  | Traffic Management | TC323130 | Left Turn Signals (Auto related) | Left turn improvements installed |  | Signalized Intersection | 3 | 1 |  | 1 |  |  | 0 |  |  | 1 |  |  |  | 3
Corridor and Intersection Improvements |  |  |  | Traffic Management | TC323130 | Left Turn Signals (Auto related) | Left turn signal improvements evaluated |  | Intersections | 20 | 6 |  | 2 |  |  | 12 |  |  | 0 |  |  |  | 20
Corridor and Intersection Improvements |  |  |  | Traffic Management | TC323610 | New Traffic Signals | New signals installed |  | Count | 4 | 0 |  | 2 |  |  | 0 |  |  | 2 |  |  |  | 4
Page 1 of 4
Program |  |  |  | Division | Project # | Project Name | Accomplishment |  | Unit of Measure | Work Plan Target | Q1 Total |  | Q2 Total |  |  | Q3 Total |  |  | Q4 Total |  |  |  | YTD Total
Corridor and Intersection Improvements |  |  |  | Traffic Management | TC323610 | New Traffic Signals | New traffic signal requests evaluated |  | Count | 50 | 21 |  | 18 |  |  | 25 |  |  | 0 |  |  |  | 64
Corridor and Intersection Improvements |  |  |  | Traffic Management | TC323860 | Collision Evaluation Program | Safety concerns investigated |  | Count | 55 | 16 |  | 8 |  |  | 11 |  |  | 19 |  |  |  | 55
Corridor and Intersection Improvements |  |  |  | Policy and Planning | TC366860 | Transit Corridor Projects | Transit corridor project implementation |  | 100% Design | 3 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
Neighborhood Enhancements |  |  |  | Traffic Management | TC365770 | NSF/CRF Neighborhood Projects | Large neighborhood project implementation |  | Projects Completed | 16 | 3 |  | 6 |  |  | 5 |  |  | 2 |  |  |  | 16
Neighborhoods |  |  |  | Traffic Management | TG357110 | Safety Programs (incl safe routes to schools) | Locations improved for pedestrian safety |  | Count | 10 | 0 |  | 3 |  |  | 4 |  |  | 4 |  |  |  | 11
Neighborhoods |  |  |  | Traffic Management | TG357100 | Implement Pedestrian Master Plan | Projects Implemented |  | Count | 25 | 6 |  | 4 |  |  | 8 |  |  | 7 |  |  |  | 25
Neighborhoods |  |  |  | Traffic Management | TG357110 | Safety Programs (incl safe routes to schools) | Walking routes to schools improved for safety |  | Number of Schools | 6 | 1 |  | 0 |  |  | 5 |  |  | 0 |  |  |  | 6
Roads |  |  |  | Capital Projects and Roadway Structures | TC365440 | Arterial Asphalt and Concrete Program | Roads paved |  | Lane Miles | 20 | 0 |  | 1.3 |  |  | 10.3 |  | 10.3 | 17.1 |  |  |  | 28.7
Sidewalk Maintenance |  |  |  | Street Maintenance | TC365120 | Sidewalk Safety Repair | Sidewalks repaired |  | Square Feet/ Block Equivalent | 44,000/22 | 3069 | / | 19213.5 |  | / | 14018.5 |  | / | 11683 |  | / |  | 47984 |  | /
[11 empty] | 1.53 |  |  | 9.61 |  |  | 7.01 |  |  | 5.84 |  |  |  | 23.99
Sidewalks and Pedestrian Facilities |  |  |  | Traffic Management | TC366480 | Sidewalk Development Program | Sidewalks built |  | Block Equivalent | 25 | 0 |  | 5.15 |  |  | 10.65 |  |  | 10.05 |  |  |  | 25.85
Signal Major Maintenance |  |  |  | Traffic Management | TG356540 | Pedestrian Countdown Signals | Pedestrian countdown signals installed |  | Intersections | 40 | 18 |  | 14 |  |  | 6 |  |  | 2 |  |  |  | 40
Page 2 of 4
Program |  |  |  | Division | Project # | Project Name | Accomplishment |  | Unit of Measure | Work Plan Target | Q1 Total |  | Q2 Total |  |  | Q3 Total |  |  | Q4 Total |  |  |  | YTD Total
Signs and Markings |  |  |  | Traffic Management | TG355310 | Curb and Pavement Marking | Arterials restriped (plus edgelines) |  | Lane Line Miles | 1300 | 58.18 |  | 756.36 |  |  | 504.55 |  |  | 3.67 |  |  |  | 1322.77
Signs and Markings |  |  |  | Traffic Management | TG356470 | Guardrail and Crash Cushion Rehabilitation | Crash cushions replaced |  | Count | 2 | 0 |  | 0 |  |  | 0 |  |  | 2 |  |  |  | 2
Signs and Markings |  |  |  | Traffic Management | TG355310 | Curb and Pavement Marking | Crosswalks remarked |  | Count | 700 | 58 |  | 291 |  |  | 251 |  |  | 210 |  |  |  | 810
Signs and Markings |  |  |  | Traffic Management | TG356470 | Guardrail and Crash Cushion Rehabilitation | Guardrail replaced/installed |  | Linear feet | 2,000 | 1061.5 |  | 743 |  |  | 265 |  |  | 16.5 |  |  |  | 2086
Signs and Markings |  |  |  | Traffic Management | TG355330 | Sign Replacement Program | Regulatory street signs replaced |  | Count | 6,625 | 1529 |  | 1506 |  |  | 3277 |  |  | 1821 |  |  |  | 8133
Signs and Markings |  |  |  | Traffic Management | TG357120 | School Zone Signage Improvements | Signage of school zones improved |  | Number of Schools | 52 | 29 |  | 13 |  |  | 10 |  |  | 0 |  |  |  | 52
Signs and Markings |  |  |  | Traffic Management | TG355330 | Sign Replacement Program | Signs replaced within a corridor |  | Corridors | 1 | 0 |  | 0 |  |  | 0 |  |  | 1 |  |  |  | 1
Signs and Markings |  |  |  | Traffic Management | TG355330 | Sign Replacement Program | Street name signs replaced |  | Intersections | 1700 | 447 |  | 528 |  |  | 553 |  |  | 187 |  |  |  | 1716
Structures Maintenance |  |  |  | Capital Projects and Roadway Structures | TG356820 | Bridge/Structure Maintenance | Bridge repair requests completed |  | Count | 350-400 | 170 |  | 85 |  |  | 106 |  |  | 38 |  |  |  | 399
Structures Maintenance |  |  |  | Capital Projects and Roadway Structures | TG356820 | Stairway/Structure Maintenance | Stairways rehabilitated |  | Count | 4-6 | 0 |  | 0 |  |  | 3 |  |  | 1 |  |  |  | 4
Traffic Signals |  |  |  | Traffic Management | TG355410 | Traffic Signals Maintenance | Signal beacon maintained |  | Count | 281 | 0 |  | 276 |  |  | 0 |  |  | 5 |  |  |  | 281
Traffic Signals |  |  |  | Traffic Management | TG355410 | Traffic Signals Operations | Traffic control cabinets replaced |  | Count | 10 | 3 |  | 1 |  |  | 6 |  |  | 0 |  |  |  | 10
Page 3 of 4
Program |  |  |  | Division | Project # | Project Name | Accomplishment |  | Unit of Measure | Work Plan Target | Q1 Total |  | Q2 Total |  |  | Q3 Total |  |  | Q4 Total |  |  |  | YTD Total
Traffic Signals |  |  |  | Traffic Management | TG355410 | Traffic Signals Maintenance | Traffic signals maintained |  | Maintenance Events | 1,027 | 108 |  | 355 |  |  | 396 |  |  | 182 |  |  | 182 | 1041
Trails and Bike Paths |  |  |  | Traffic Management | TC366891 | Urban Trail and Bikeway Spot Improvements | Bicycle Facility Maintenance |  | Lane Miles | 35 | 0 |  | 36.11 |  |  | 11.97 |  |  | 0 |  |  |  | 48.07
Trails and Bike Paths |  |  |  | Traffic Management | TC366760 | Bike Master Plan Implementation | Bike lanes and sharrows striped |  | Miles | 35 | 0 |  | 7.06 |  |  | 21.26 |  |  | 6.65 |  |  |  | 35.32
Trails and Bike Paths |  |  |  | Traffic Management | TC366760 | Bike Master Plan Implementation | Bike route signs installed |  | Miles of bike routes | 19 | 4.3 |  | 3.3 |  |  | 3.3 |  |  | 0.87 |  |  |  | 19.6
Trails and Bike Paths |  |  |  | Traffic Management | TC366760 | Bike Master Plan Implementation | Bike trail segments built |  | Count | 2 | 0 |  | 1 |  |  | 1 |  |  | 0 |  |  |  | 2
Trails and Bike Paths |  |  |  | Traffic Management | TC366760 | Bike Master Plan Implementation | Trail inspection |  | Miles of trails | 20 | 20 |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 20
Trails and Bike Paths |  |  |  | Traffic Management | TC366890 | Urban Trail and Bikeway Maintenance | Urban trail and bikeway spot improvements |  | Count | 46 | 5 |  | 19 |  |  | 23 |  | 0 | 0 |  |  |  | 47
Tree and Landscape Maintenance |  |  |  | Street Use and Urban Forestry | TG352050 | Landscape Maintenance | Landscape maintenance |  | Square feet 1 acre equiv | 43,560 | 24200 |  | 0 |  |  | 17561 |  |  | 2250 |  |  |  | 44011
Tree and Landscape Maintenance |  |  |  | Street Use and Urban Forestry | TG356810 | Arborist Services | Trees planted |  | Count | 800 | 180 |  | 499 |  |  | 0 |  |  | 139 |  |  |  | 818
Tree and Landscape Maintenance |  |  |  | Street Use and Urban Forestry | TG356810 | Arborist Services | Trees pruned |  | Count | 3000 | 547 |  | 520 |  |  | 1943 |  |  | 559 |  |  |  | 3569
Page 4 of 4