## Sheet1
Seattle Department of Transportation
Bridging the Gap Planned Accomplishments
Year: 2011 | [5 empty] | Annual target has been met |  |  | 40 accomplishment types are green
Run Date: 12/08/2011 | [5 empty] | Annual target is on track to be met |  |  | 0 accomplishment types are light green
Division: All | [5 empty] | Annual target is on track with caution |  |  | 0 accomplishment types are yellow
Program: All | [5 empty] | Annual target will not be met |  |  | 0 accomplishment types are red
Program | Division | Project # | Project Name | Accomplishment | Unit of Measure | Work Plan Target | Q1 Total | Q2 Total | Q3 Total | Q4 Total | YTD Total
Commuter Mobility | Traffic Management |  | Traffic Operations Spot Improvements - Signals | Electrical traffic control devices evaluated | Count | 225 | 112 | 34 | 76 | 6 | 228
Commuter Mobility | Traffic Management |  | Traffic Operations Spot Improvements - Signals | Electrical traffic control devices installed, modified or removed | Count | 50 | 19 | 37 | 19 | 4 | 79
Commuter Mobility | Policy and Planning |  | Transit Service | Secured transit hours | Maintain | 44000 | 0 | 0 | 0 | 0 | 44,000
Commuter Mobility | Traffic Management |  | Traffic Operations Spot Improvements | Speed watch trailer deployed | Times | 50 | 10 | 15 | 3 | 23 | 51
Commuter Mobility | Traffic Management |  | Traffic Operations Spot Improvements | Traffic control concerns evaluated | Count | 550 | 237 | 162 | 177 | 343 | 919
Corridor and Intersection Improvements | Traffic Management |  | Left Turn Signals (auto related) | Left turn improvements installed | Signalized Intersection | 2 | 0 | 1 | 0 | 1 | 2
Corridor and Intersection Improvements | Traffic Management |  | Left Turn Signals (auto related) | Left turn signal improvements evaluated | Intersections | 40 | 5 | 14 | 12 | 9 | 40
Corridor and Intersection Improvements | Traffic Management |  | New Traffic Signals | New signals installed | Count | 3 | 0 | 1 | 1 | 1 | 3
Corridor and Intersection Improvements | Traffic Management |  | New Traffic Signals | New traffic signal requests evaluated | Count | 50 | 16 | 17 | 20 | 0 | 53
Program | Division | Project # | Project Name | Accomplishment | Unit of Measure | Work Plan Target | Q1 Total | Q2 Total | Q3 Total | Q4 Total | YTD Total
Corridor and Intersection Improvements | Traffic Management |  | Collision Evaluation Program | Safety concerns investigated | Count | 35 | 11 | 11 | 8 | 5 | 35
Corridor and Intersection Improvements | Policy and Planning |  | Transit Corridor Projects | Transit corridor project implementation | Milestones | 3 | 0 | 0 | 0 | 0 | 3
Neighborhood Enhancements | Traffic Management |  | NSF/CRF neighborhood project implementation | Large neighborhood project implementation | Design projects | 11 | 1 | 0 | 0 | 10 | 11
Neighborhoods | Traffic Management |  | Pedestrian Master Plan Implementation | Crossing improvements implemented | Count | 50 | 8 | 12 | 16 | 15 | 51
Neighborhoods | Traffic Management |  | Pedestrian Master Plan - School Safety | Walking routes to schools improved for safety | Number of Schools | 5 | 0 | 2 | 2 | 2 | 6
Roads | Capital Projects and Roadway Structures |  | Arterial Asphalt and Concrete Program | Roads paved | Lane miles | 24 | 0 | 0 | 0 | 24 | 24
Sidewalk Maintenance | Street Maintenance |  | Sidewalk Safety Repair | Sidewalks repaired | Block Equivalent | 22 | 6.51 | 3.37 | 9.43 | 5.75 | 25.06
Signal Major Maintenance | Traffic Management |  | Pedestrian Countdown Signals | Pedestrian Countdown signals installed | Intersections | 25 | 9 | 6 | 10 | 1 | 26
Signs and Markings | Traffic Management |  | Curb and Pavement Marking | Arterials restriped (plus edge lines) | Lane Line Miles | 1148 | 32.23 | 423.01 | 550.65 | 145.16 | 1151.05
Signs and Markings | Traffic Management |  | Guardrail and Crash Cushion Rehabilitation | Crash cushions replaced | Count | 2 | 2 | 0 | 0 | 0 | 2
Signs and Markings | Traffic Management |  | Curb and Pavement Marking | Crosswalks remarked | Count | 300 | 57 | 108 | 136 | 5 | 306
Signs and Markings | Traffic Management |  | Guardrail and Crash Cushion Rehabilitation | Guardrail replaced/installed | Linear feet | 1886 | 1037 | 854 | 0 | 25 | 1916
Signs and Markings | Traffic Management |  | Sign Replacement Program | Regulatory street signs replaced | Count | 4500 | 2155 | 1130 | 647 | 768 | 4700
Program | Division | Project # | Project Name | Accomplishment | Unit of Measure | Work Plan Target | Q1 Total | Q2 Total | Q3 Total | Q4 Total | YTD Total
Signs and Markings | Traffic Management |  | Pedestrian Master Plan - School Safety | Signage of School Zones Improved | Number of Schools | 10 | 0 | 5 | 5 | 0 | 10
Signs and Markings | Traffic Management |  | Sign Replacement Program | Street name signs replaced | Intersections | 1154 | 452 | 452 | 138 | 113 | 1155
Structures Maintenance | Capital Projects and Roadway Structures |  | Bridge/Structure Maintenance | Bridge repair requests completed | Count | 189 | 66 | 38 | 45 | 72 | 221
Structures Maintenance | Capital Projects and Roadway Structures |  | Stairway/Structure Maintenance | Stairways rehabilitated | Count | 3 | 0 | 0 | 2 | 1 | 3
Traffic Signals | Traffic Management |  | Traffic Signal Operations | Traffic control cabinets replaced | Count | 6 | 2 | 2 | 4 | 0 | 8
Traffic Signals | Traffic Management |  | Traffic Signal Maintenance | Traffic signals maintained | Maintenance Events | 1050 | 313 | 357 | 313 | 72 | 1055
Trails and Bike Paths | Traffic Management |  | Urban Trail and Bikeway Spot Improvements | Bicycle facility maintenance | Lane miles | 25.5 (30)* | 0 | 18.37 | 7.9 | 0 | 26.27
Trails and Bike Paths | Traffic Management |  | Bike Spot Safety Improvements | Bicycle parking (racks) | spaces | 210 (300)* | 120 | 4 | 30 | 56 | 210
Trails and Bike Paths | Traffic Management |  | Bike Master Plan Implementation | Bike lanes and sharrows striped | Miles | 15 | 0.25 | 2.35 | 12.42 | 0 | 15.02
Trails and Bike Paths | Traffic Management |  | Bike Master Plan Implementation | Bike route signs installed | Miles of bike routes | 30 | 3.8 | 13.8 | 5.2 | 8.7 | 31.5
Trails and Bike Paths | Traffic Management |  | Bike Master Plan Implementation | Bike trail segments built | Count | 1 | 0 | 0 | 0 | 1 | 1
Trails and Bike Paths | Traffic Management |  | Pedestrian Master Plan Implementation | Design and coordinate construction new curb ramps | Count | 280 | 7 | 24 | 178 | 86 | 295
Trails and Bike Paths | Traffic Management |  | Pedestrian Master Plan Implementation | Sidewalks built | Block equivalent | 10 | 0 | 1.5 | 1.5 | 7 | 10
Program | Division | Project # | Project Name | Accomplishment | Unit of Measure | Work Plan Target | Q1 Total | Q2 Total | Q3 Total | Q4 Total | YTD Total
Trails and Bike Paths | Traffic Management |  | Bike Master Plan Implementation | Trail Inspection | Miles of trails | 20 | 27 | 0 | 0 | 0 | 27
Trails and Bike Paths | Traffic Management |  | Urban Trail and Bikeway Spot Improvements | Urban trail and bikeway spot improvements | Count | 9 (15)* | 3 | 0 | 7 | 0 | 10
Tree and Landscape Maintenance | Street Use and Urban Forestry |  | Landscape Maintenance | Landscape maintenance | Maintenance Events | 840 | 247 | 282 | 221 | 133 | 883
Tree and Landscape Maintenance | Street Use and Urban Forestry |  | Arborist Service | Trees planted | Count | 800 | 503 | 82 | 0 | 231 | 816
Tree and Landscape Maintenance | Street Use and Urban Forestry |  | Arborist Service | Trees pruned | Count | 3000 | 760 | 445 | 414 | 1715 | 3334
* Work plan target reduce due to mid-year budget cuts