## Sheet1
This example cost estimate has not been reviewed or approved for wide use. It is provided as informational only. The engineer may use this, but it should be thoroughly checked.
Pump Station Cost Estimate
|  | General man-day cost | 336
|  | Electrical contractor man-day cost | 400
|  |  |  | Material |  |  |  | Equipment
|  |  | Material | Unit | Material | Material | Equip. | Unit | Equip. | Equipment |  |  | Labor | Subtotal | Percent |  | Item | Total
Description |  |  | Units | Price | Quantity | Cost | Units | Price | Quantity | Cost | Crew | Days | Cost | Cost | OH&P | OH&P | Total | Cost
1 | Mobilization and Demobilization
2 | Temporary Construction Pump Station & Site Work
Temporary Submersible Pumps
Temporary Above-grade Piping
Site Excavation
Site Restoration
3 | Mechanical | (including removal)
Remove Existing Pumps & Valves
Install New Centrifugal Pumps
Install pump pads
Check Valves
Gate Valves
Eccentric Plug Valves
Combination air release valve
Suction and Discharge Piping
Ventilation
Hatch
Grating modifications
Flexible coupling
Pipe support
Magmeter
Suction and Discharge pressure gauge
4 | Structural
Valve Vault
Dry Well/Wet Well Structure
Pump Base
5 | Electrical Equipment, Power Supply, Controls and Instrumentation
Remove Existing MCC
New Motor Control Center
Temporary Power Supply to Temp Pumps
Telemetry
SCADA
Conduit Installation
Testing and Start-up
[5 empty] | Materials Total |  |  |  | Equipment Total |  |  | Labor Total |  |  | OH&P Total
Construction Costs
Contingency @ *
Construction Costs w/ Const. Contigency
Washington State Sales Tax
Construction with Contingency & SST
Design Engineering & Bidding Phase (15%)
Permitting (1%)
Construction Engineering and Administration (15%)
Indirect Cost Subtotal
Project Cost Including Const. and Indirect Costs
Project Contingency (*)
Total Estimated Project Cost
* Use percentages developed from risk register
Note on O12: Move in, fencing, survey, move out, and clean up
Note on E41: Lights, receptacles, conduit and wire. MTS, utility meter,